## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set up the basic structure of the Flask application | MUST HAVE | Flask Framework | Arundhati Rothe | Completed
S1 | S1 | US-002 | Design the web interface for the chatbot using HTML/CSS | MUST HAVE | HTML, CSS, JavaScript | Arundhati Rothe | Completed
S2 | S2 | US-003 | Integrate Groq API for AI-powered responses | MUST HAVE | Groq API, Python | Arundhati Rothe | Completed
S2 | S2 | US-004 | Develop database schema and setup MySQL integration | MUST HAVE | MySQL, Flask SQLAlchemy | Arundhati Rothe | Completed
S3 | S3 | US-005 | Add conversational context to the chatbot responses | MUST HAVE | BERT, Sentence Transformers | Arundhati Rothe | Completed
S3 | S3 | US-006 | Build user registration and authentication system | MUST HAVE | Flask-Login, MySQL | Arundhati Rothe | Completed
S4 | S4 | US-007 | Add file upload feature for patient reports | MUST HAVE | Werkzeug, Flask | Arundhati Rothe | Completed
S4 | S4 | US-008 | Create additional pages | MUST HAVE | HTML, CSS | Arundhati Rothe | Completed
S5 | S5 | US-009 | Implement security for API keys and sensitive data | MUST HAVE | Python Dotenv | Arundhati Rothe | Completed
S6 | S6 | US-010 | Deploy application using Flask in LocalHost | MUST HAVE | Flask Development Server | Arundhati Rothe | Completed
S7 | S7 | US-011 | Perform rigorous testing for various edge cases | MUST HAVE | Test Cases, Groq API | Arundhati Rothe | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 152 | 41 | 36 | 28 | 25 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | US IDTask IDTask DescriptionTask Start DateTask Completion DateTeam MemberActivity StatusOriginal Estimate (Hours)US-001TID-01Set up Flask application9-Dec-2411-Dec-24Arundhati RotheDevelopment8US-002TID-01Design web-based chatbot interface with HTML/CSS12-Dec-2414-Dec-24Arundhati RotheUI/UX Design10US-003TID-01Integrate Groq API for chatbot responses15-Dec-2418-Dec-24Arundhati RotheIntegration12US-004TID-01Database schema setup and MySQL integration19-Dec-2422-Dec-24Arundhati RotheDatabase Design14US-005TID-01Add conversational context to chatbot responses23-Dec-2429-Dec-24Arundhati RotheNLP Implementation20US-006TID-01Build user authentication system30-Dec-243-Jan-25Arundhati RotheDevelopment15US-007TID-01Add file upload feature for patient reports4-Jan-258-Jan-25Arundhati RotheFeature Development12US-008TID-01Create Home, Login, Register & index pages9-Jan-2513-Jan-25Arundhati RotheFrontend Design10US-009TID-01Implement security for API keys and sensitive data14-Jan-2518-Jan-25Arundhati RotheSecurity14US-010TID-01Deploy application using Flask in LocalHost19-Jan-2523-Jan-25Arundhati RotheDeployment12US-011TID-01Perform rigorous testing for edge cases24-Jan-2525-Jan-25Arundhati RotheTesting15US-012TID-01Optimize chatbot model for speed and accuracy26-Jan-2528-Jan-25Arundhati RotheOptimization10 | Task Completion Date | Team Member | Activity Status | Original Estimate (Hours) | 8 | 3 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-01 | Set up Flask application | 2024-12-09 | 2024-12-11 | Arundhati Rothe | Development | 8 | 10 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-01 | Design Streamlit-based chatbot interface | 2024-12-12 | 2024-12-14 | Arundhati Rothe | UI/UX Design | 10 | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-01 | Integrate Groq API for chatbot responses | 2024-12-15 | 2024-12-18 | Arundhati Rothe | Integration | 12 | 14 | 4 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-01 | Database schema setup and MySQL integration | 2024-12-19 | 2024-12-22 | Arundhati Rothe | Database Design | 14 | 20 | 4 | 4 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-01 | Add conversational context to chatbot responses | 2024-12-23 | 2024-12-29 | Arundhati Rothe | NLP Implementation | 20 | 15 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-01 | Build user authentication system | 2024-12-30 | 2025-01-03 | Arundhati Rothe | Development | 15 | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-01 | Add file upload feature for patient reports | 2025-01-04 | 2025-01-08 | Arundhati Rothe | Feature Development | 12 | 10 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-01 | Create Home, Login, Register & index pages | 2025-01-09 | 2025-01-13 | Arundhati Rothe | Frontend Design | 10 | 14 | 4 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TID-01 | Implement security for API keys and sensitive data | 2025-01-14 | 2025-01-18 | Arundhati Rothe | Security | 14 | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TID-01 | Deploy application using Flask in LocalHost | 2025-01-19 | 2025-01-23 | Arundhati Rothe | Deployment | 12 | 15 | 4 | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TID-01 | Perform rigorous testing for edge cases | 2025-01-24 | 2025-01-25 | Arundhati Rothe | Testing | 15 | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Difficulty understanding user requirements for chatbot design | Conducted a requirements gathering workshop with stakeholders to clarify expectations.
Sprint 1 | Day 8 | Unfamiliarity with integrating third-party APIs | Referred to API documentation and conducted hands-on practice sessions to build expertise.
Sprint 2 | Day 11 | Errors in setting up the database schema for the project | Reviewed database design with a mentor and corrected schema inconsistencies.
Sprint 3 | Day 15 | Delays in implementing user authentication features | Collaborated with the team to divide tasks and expedite the development process.
Sprint 4 | Day 20 | UI inconsistencies across different screen resolutions | Conducted cross-platform testing and fixed UI responsiveness issues.

## Retrospection
Sprint # | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken | Action taken
Sprint 1 | 2024-12-09 | 2024-12-15 | Arundhati Rothe | Focus on API integration | Delaying code reviews | Sharing progress regularly | Conducted hands-on practice sessions for API usage. | Conducted hands-on practice sessions for API usage.
Sprint 2 | 2024-12-16 | 2024-01-21 | Arundhati Rothe | Testing features more rigorously | Ignoring minor bugs | Collaborating with mentors | Scheduled a team debugging session to resolve persistent errors. | Scheduled a team debugging session to resolve persistent errors.
Sprint 3 | 2024-12-22 | 2024-12-27 | Arundhati Rothe | Documenting workflow improvements | Skipping retrospective meetings | Prioritizing critical tasks | Created documentation templates for improved consistency. | Created documentation templates for improved consistency.
Sprint 4 | 2024-12-28 | 2025-01-02 | Arundhati Rothe | Tracking UI responsiveness issues | Assuming browser compatibility | Cross-platform testing | Resolved UI inconsistencies for different screen resolutions. | Resolved UI inconsistencies for different screen resolutions.
Sprint 5 | 2025-01-03 | 2025-01-08 | Arundhati Rothe | Optimizing model performance | Postponing optimization tasks | Improving communication | Utilized advanced ML techniques to fine-tune model accuracy. | Utilized advanced ML techniques to fine-tune model accuracy.
Sprint 6 | 2025-01-09 | 2025-01-14 | Arundhati Rothe | Conducting user feedback sessions | Neglecting user feedback | Enhancing system usability | Integrated user feedback into the design process. | Integrated user feedback into the design process.
Sprint 7 | 2025-01-20 | 2025-01-28 | Arundhati Rothe | Planning long-term scalability | Overlooking scalability concerns | Strengthening team collaboration | Developed a roadmap for scaling the application. | Developed a roadmap for scaling the application.